## 1. Executive Summary
Africa Consumer Price Index (CPI) Collector
Progress Report — work done, challenges & remedies, and outstanding items
Generated: 2026-07-14
Objective
Collect CPI/inflation data for all 54 African countries EXACTLY as reported by each National Statistics Office (NSO)
— no estimation, no imputation, no omission. Native (non-COICOP) classifications are kept as reported; every
published period is emitted; the original source document is retained for audit.
Headline status
41 of 54 countries collected (76%).
- 37 full division-level captures (COICOP-1999 / COICOP-2018 / native nomenclature).
- 2 all-items (headline) captures where the NSO publishes no clean division breakdown (Angola, Liberia).
- 2 documented partial captures (DR Congo — annual to 2020; Ethiopia — all-items, fiscal-year dates).
3 of the 41 use a sanctioned CENTRAL-BANK fallback that republishes the NSO's own CPI (DR Congo, Libya, Mozambique).
13 countries outstanding — server outages, auth-gated APIs, or no CPI published online (see sheet 4).
Approach
Per country: a declarative descriptor (YAML) + a small parser. A shared pipeline handles discover -> download ->
extract -> parse -> validate -> write one tidy CSV, and one country breaking never stops the others.
17 reusable discovery methods were built to reach data behind APIs, CMS platforms and SPAs (WordPress, Joomla,
Liferay, Nuxt, Angular, Laravel/Node). Full method & pattern catalogue in DEVELOPER_GUIDE.md.
Key achievements
Cracked heavily-gated modern sites by reverse-engineering their backend APIs from JS bundles.
Recovered 'written-off' countries: Libya & Mozambique via their central banks; Burundi via an agency rebrand (INSBU).
Reach spans Tier-1 API (Ghana), Tier-2 Excel, and Tier-3 PDF scrapes with robust table extraction.
Deep history where published: Ghana 337 months, Senegal 342, Namibia 294, Seychelles 230, Mozambique 126.

## 2. Country Status
# | Country | ISO3 | Region / Bloc | Status | Source of record | Classification | Months | Period range | Div. series | Measures | Access / discovery method | Key challenge | Remedy applied
1 | Algeria | DZA | North Africa | Complete — full | NSO (ONS) | Native 8-group | 1 | 2026-04 to 2026-04 | 9 | index,inflation_mom,inflation_yoy | page_scrape | NOT COICOP — native nomenclature; label wraps | Captured native 8 groups as-reported; positional parse
2 | Angola | AGO | Southern (SADC) | Complete — all-items | NSO (INE) | All-items (YoY) | 127 | 2015-12 to 2026-06 | 1 | inflation_yoy | regex_on_page | Time-series DB; .xlsx path baked into obfuscated JS | regex_on_page; headline series only (no divisions in DB)
3 | Benin | BEN | West Africa (WAEMU) | Complete — full | NSO (INStaD) | COICOP-2018 | 324 | 1998-01 to 2024-12 | 14 | index | page_scrape | Same WAEMU IHPC Excel; different sheet name | Reused waemu_ihpc parser
4 | Botswana | BWA | Southern (SADC) | Complete — full | NSO (Stats Botswana) | COICOP-1999 | 5 | 2025-05 to 2026-05 | 13 | index | page_scrape | Period columns leaked onto the rates table | Scope parsing to the 'national CPI group' pages
5 | Burkina Faso | BFA | West Africa (WAEMU) | Complete — full | NSO (INSD) | COICOP-2018 | 1 | 2026-05 to 2026-05 | 14 | index,inflation_mom,inflation_yoy | page_scrape | IHPC note as .xlsx/.xls 'Tableau 1' | page_scrape + Excel note parser
6 | Burundi | BDI | East Africa (EAC) | Complete — full | NSO (INSBU) | COICOP-1999 | 1 | 2026-06 to 2026-06 | 13 | index,inflation_mom,inflation_yoy | insbu_latest | Old domain hijacked; agency rebranded ISTEEBU->INSBU | Web-searched rebrand; insbu_latest Laravel API
7 | Cameroon | CMR | Central Africa (CEMAC) | Complete — full | NSO (INS) | COICOP-1999 | 1 | 2026-05 to 2026-05 | 13 | index,inflation_mom,inflation_yoy | two_hop_scrape | Messy CEMAC PDF; wrapped function labels | Positional/bbox extraction; two_hop discovery
8 | Central African Rep. | CAF | Central Africa (CEMAC) | Complete — full | NSO (ICASEES) | COICOP-1999 | 1 | 2025-07 to 2025-07 | 13 | index,inflation_mom,inflation_yoy | edocman_latest | Joomla Edocman; N° resets yearly; interleaved sub-items | edocman_latest; sort by (year,month); own-vs-window rule
9 | Chad | TCD | Central Africa (CEMAC) | Complete — full | NSO (INSEED) | COICOP-1999 | 1 | 2026-05 to 2026-05 | 13 | index,inflation_mom,inflation_yoy | inseed_tchad_latest | SPA over a Node API; Roman-numeral labels; summary-block clash | inseed_tchad_latest; Roman lookahead; require weight 10000
10 | Congo (Rep.) | COG | Central Africa (CEMAC) | Complete — full | NSO (INS) | COICOP-1999 | 1 | 2026-05 to 2026-05 | 13 | index,inflation_mom,inflation_yoy | wpdm_latest | WordPress Download-Monitor; labels wrap above+below | wpdm_latest (?wpdmdl=); prev+own+next window
11 | Cote d'Ivoire | CIV | West Africa (WAEMU) | Complete — full | NSO (ANStat) | COICOP-2018 | 1 | 2026-06 to 2026-06 | 14 | index,inflation_mom,inflation_yoy | anstat_ci_ihpc | Dead old domain; real site SPA w/ ephemeral hashes + bad cert | Found anstat.ci; PDF path deterministic from thumbnail id
12 | DR Congo | COD | Central Africa | Complete — partial (documented) | Central Bank (BCC) | All-items (annual) PARTIAL | 29 | 1992-12 to 2020-12 | 1 | index,inflation_yoy | - | NSO (INS-RDC) WAF-blocked; only annual CB file to 2020 | CB fallback; annual index dated YYYY-12; flagged partial
13 | Egypt | EGY | North Africa | Complete — full | NSO (CAPMAS) | COICOP-1999 | 1 | 2026-06 to 2026-06 | 13 | index,inflation_mom,inflation_yoy | capmas_publication | SPA backed by a JSON API on a non-standard port | Reverse-engineered CAPMAS publication API (excel/pdf per issue)
14 | Ethiopia | ETH | Horn of Africa | Complete — partial (documented) | NSO (ESS) | All-items PARTIAL | 13 | 2025-05 to 2026-05 | 1 | inflation_mom,inflation_yoy | page_scrape | Divisions chart-only; Ethiopian fiscal-year dates | Capture headline YoY+MoM; EFY->Gregorian; anchor last row
15 | Ghana | GHA | West Africa | Complete — full | NSO (GSS StatsBank) | COICOP-2018 | 337 | 1998-01 to 2026-01 | 14 | index,inflation_mom,inflation_yoy | api | None — Tier-1 PxWeb API available | Native PxWeb JSON client (best-case source)
16 | Guinea | GIN | West Africa | Complete — full | NSO (INS) | COICOP-1999 | 1 | 2026-05 to 2026-05 | 13 | index,inflation_mom,inflation_yoy | page_scrape | Comma-decimals, thousands-spaces, 3-line wrapped labels | Scope to national 'par fonction' page; window labels
17 | Kenya | KEN | East Africa (EAC) | Complete — full | NSO (KNBS) | COICOP-2018 (rates) | 1 | 2026-06 to 2026-06 | 14 | inflation_mom,inflation_yoy | latest_dated | PDF-only; letter-spaced headers; CBK fallback needed if KNBS down | latest_dated discovery; positional row parse; documented CBK fallback
18 | Lesotho | LSO | Southern (SADC) | Complete — full | NSO (BOS) | COICOP-1999 | 1 | 2026-05 to 2026-05 | 13 | index,inflation_mom,inflation_yoy | latest_dated | Integer weight (100) broke decimal-only counts; wrapped label | Require >=5 numbers; trailing anchor; pending-label
19 | Liberia | LBR | West Africa | Complete — all-items | NSO (LISGIS) | All-items (idx+rates) | 13 | 2025-05 to 2026-05 | 1 | index,inflation_mom,inflation_yoy | latest_dated | By-division figures published only as bar charts | Capture clean 'Table 1' all-items series; document gap
20 | Libya | LBY | North Africa | Complete — full | Central Bank (CBL) | COICOP-1999 | 29 | 2024-01 to 2026-05 | 13 | index,inflation_yoy | page_scrape | Conflict state; no reachable NSO site | CB fallback: CBL republishes NSO CPI (full index by group)
21 | Madagascar | MDG | Southern (SADC)/Islands | Complete — full | NSO (INSTAT) | COICOP-1999 | 123 | 2016-01 to 2026-03 | 13 | index | two_hop_scrape | SPA (Laravel); .xlsx hidden behind monthly page | two_hop_scrape to /documents/upload/main/*.xlsx
22 | Malawi | MWI | Southern (SADC) | Complete — full | NSO (NSO) | COICOP-1999 | 26 | 2024-04 to 2026-05 | 13 | index,inflation_mom | malawi_cms_cpi | Nuxt SPA over a Laravel headless CMS | malawi_cms_cpi: /api/web/news list -> attachment
23 | Mali | MLI | West Africa (WAEMU) | Complete — full | NSO (INSTAT) | COICOP-2018 | 5 | 2025-06 to 2026-06 | 14 | index | page_scrape | extract_tables split the national table across pages | Pure text parser; handle thousands-space '10 000'
24 | Mauritania | MRT | North/West Africa | Complete — full | NSO (ANSADE) | COICOP-1999 (local) | 1 | 2026-06 to 2026-06 | 13 | index,inflation_mom,inflation_yoy | wp_media_latest | SPA over WordPress backend | wp_media_latest on admin.ansade.mr media API
25 | Mauritius | MUS | Southern (SADC)/Islands | Complete — full | NSO (Stats Mauritius) | COICOP-2018 | 2 | 2026-05 to 2026-06 | 14 | index | page_scrape | Monthly note 'Division' table | page_scrape; 2-month index parse
26 | Morocco | MAR | North Africa | Complete — full | NSO (HCP) | COICOP-1999 | 113 | 2017-01 to 2026-05 | 13 | index | gsheet_from_page | Data embedded as a Google Sheet, one tab per series | gsheet_from_page: build a whole-workbook xlsx export URL
27 | Mozambique | MOZ | Southern (SADC) | Complete — full | Central Bank (BM) | COICOP-1999 | 126 | 2016-01 to 2026-06 | 13 | index | two_hop_scrape | NSO (INE) Liferay auth-gated (403) | CB fallback: BM republishes INE's full CPI xls (2016-)
28 | Namibia | NAM | Southern (SADC) | Complete — full | NSO (NSA) | COICOP-1999 | 294 | 2002-01 to 2026-06 | 13 | index,inflation_mom,inflation_yoy | two_hop_scrape | Two-hop: category archive -> doc page -> xlsx | two_hop_scrape; wide series (2002-)
29 | Niger | NER | West Africa (WAEMU) | Complete — full | NSO (INS) | COICOP-2018 | 1 | 2026-06 to 2026-06 | 14 | index,inflation_mom,inflation_yoy | page_scrape | IHPC note PDF | page_scrape; nums[-4]/-3/-1 pattern
30 | Nigeria | NGA | West Africa | Complete — full | NSO (NBS) | COICOP-2018 | 41 | 2023-01 to 2026-05 | 14 | index | catalog_latest | Excel buried inside a monthly ZIP in a data catalogue | catalog_latest discovery + unzip; parse 'Table2' national index
31 | Rwanda | RWA | East Africa (EAC) | Complete — full | NSO (NISR) | COICOP-1999 | 3 | 2025-06 to 2026-06 | 13 | index | latest_dated_pdf | Index buried in 'Annex 3: All Rwanda' of a long PDF | latest_dated_pdf; scope to the national annex table
32 | Senegal | SEN | West Africa (WAEMU) | Complete — full | NSO (ANSD) | COICOP-2018 | 342 | 1998-01 to 2026-06 | 14 | index | page_scrape | Shared UEMOA IHPC Excel layout; sheet auto-detect | Shared waemu_ihpc parser (detect data sheet by code header)
33 | Seychelles | SYC | Islands | Complete — full | NSO (NBS) | COICOP-1999 | 230 | 2007-01 to 2026-02 | 13 | index | latest_dated | Multi-block workbook; Food/Non-food layout | latest_dated; first (index) block; keyword rows
34 | Sierra Leone | SLE | West Africa | Complete — full | NSO (Stats SL) | COICOP-1999 | 1 | 2026-05 to 2026-05 | 13 | index,inflation_mom,inflation_yoy | latest_dated | Discovery grabbed an old 2018 file; unreadable header | Switched to latest_dated; trailing-number anchor
35 | South Africa | ZAF | Southern (SADC) | Complete — full | NSO (Stats SA) | COICOP-2018 | 221 | 2008-01 to 2026-05 | 14 | index | probe_monthly | Listing page behind an Incapsula anti-bot WAF | probe_monthly: walk the dated file-URL template backward until a file exists
36 | Tanzania | TZA | East Africa (EAC) | Complete — full | NSO (NBS) | COICOP-2018 | 3 | 2025-06 to 2026-06 | 14 | index | page_scrape | 'All Items' in col0 not col1; transient site timeouts | Scan whole row text + 'less' exclusion; retry on timeout
37 | Togo | TGO | West Africa (WAEMU) | Complete — full | NSO (INSEED) | COICOP-2018 | 1 | 2026-06 to 2026-06 | 14 | index,inflation_mom,inflation_yoy | page_scrape | IHPC note PDF; 3 trailing variation columns | nums[-4]/-3/-1 trailing-anchor pattern
38 | Tunisia | TUN | North Africa | Complete — full | NSO (INS) | COICOP-1999 | 9 | 2025-10 to 2026-06 | 13 | index | static_url | Data is an HTML table, not a file | static_url + HTML table parser
39 | Uganda | UGA | East Africa (EAC) | Complete — full | NSO (UBOS) | COICOP-2018 | 108 | 2017-07 to 2026-06 | 14 | index,inflation_mom,inflation_yoy | latest_dated | Wide multi-centre Excel; national + 10 urban centres | latest_dated; parse 'Division' sheet wide series
40 | Zambia | ZMB | Southern (SADC) | Complete — full | NSO (ZamStats) | COICOP-1999 | 42 | 2023-01 to 2026-06 | 13 | index | page_scrape | Header cells wrapped across lines ('Food and\nNon-Alcoholic') | Normalise whitespace before keyword match
41 | Zimbabwe | ZWE | Southern (SADC) | Complete — full | NSO (ZimStat) | COICOP-1999 | 25 | 2024-04 to 2026-04 | 13 | index | latest_month_file | JS front-end; ZWL/ZiG/USD/Weighted currency maze | WordPress REST API; take the 'Weighted' headline series
42 | Guinea-Bissau | GNW | West Africa (WAEMU) | Outstanding — Server outage | — | — | - | — | - | — | — | NSO (INE) IHPC PDF exists but stat-guinebissau.com times out globally | Retry when server recovers (~15-min build; WAEMU format known). Thin fallbacks: BCEAO headline / MoF stale IHPC
43 | Gabon | GAB | Central Africa (CEMAC) | Outstanding — Server outage | — | — | - | — | - | — | — | NSO (DGSS) dgstat.ga unreachable; no live alternate domain | Retry later; or BEAC regional bulletin (headline only)
44 | Eswatini | SWZ | Southern (SADC) | Outstanding — Server outage | — | — | - | — | - | — | — | NSO (CSO) eswatinistats.org.sz unreachable | Retry later; CB/MoF publish only budget/headline
45 | Djibouti | DJI | Horn of Africa | Outstanding — Backend down | — | — | - | — | - | — | — | NSO Nuxt SPA -> Heroku API returns 404/500 (backend down) | Retry when backend recovers; MoF has no CPI
46 | Cabo Verde | CPV | West Africa/Islands | Outstanding — Auth-gated | — | — | - | — | - | — | — | NSO (INE) Angular API 401 everywhere, no token in client; CB/MoF publish no CPI file | Needs INE API credentials
47 | Comoros | COM | Southern/Islands | Outstanding — Weak partial only | — | — | - | — | - | — | — | NSO SPA shell; only CB quarterly bulletin (all-items IHPC, quarterly, sparse) | Optional ⚠️ partial from BCC bulletin if coverage required
48 | Sao Tome & Principe | STP | Central Africa/Islands | Outstanding — No online CPI | — | — | - | — | - | — | — | NSO Phoca-download categories empty; CB/MoF publish no CPI series | Monitor; likely needs direct request to INE
49 | Gambia | GMB | West Africa | Outstanding — No online CPI | — | — | - | — | - | — | — | NSO main site down; only a NADA microdata portal (no CPI series) | Retry NSO site; or request from GBoS
50 | Equatorial Guinea | GNQ | Central Africa (CEMAC) | Outstanding — No online CPI | — | — | - | — | - | — | — | NSO (INEGE) static shell, no files/API; CB is regional BEAC (headline only) | Monitor; BEAC headline as last resort
51 | Somalia | SOM | Horn of Africa | Outstanding — No online CPI | — | — | - | — | - | — | — | No NSO CPI; CB & MoF publish none | Out of reach
52 | Sudan | SDN | North/Horn | Outstanding — No online CPI (conflict) | — | — | - | — | - | — | — | CBOS/MoF have no CPI series online | Out of reach (conflict)
53 | South Sudan | SSD | East Africa | Outstanding — Stale only (conflict) | — | — | - | — | - | — | — | CB statistical bulletins stale to 2021 and broken PDFs | Out of reach (conflict)
54 | Eritrea | ERI | Horn of Africa | Outstanding — No online CPI | — | — | - | — | - | — | — | No NSO/CB/MoF CPI online | Out of reach

## 3. Challenges & Remedies
Challenge type | What it looks like | Remedy / tactic | Example countries
Site is a JavaScript SPA (empty HTML shell) | Home page is 1–10 KB; no data or links in the HTML | Fetch the JS bundles, grep for the backend API base, call its list endpoint, read the file-URL field | Malawi, Chad, Mauritania, Burundi, Madagascar, Cote d'Ivoire
Anti-bot WAF (403 / 406) | Bare requests rejected; sometimes 200 with empty body | Send a full Chrome User-Agent + Accept/Accept-Language headers | Mauritania (406), several
Incomplete TLS certificate chain | requests needs verify=False; headless browser refuses | Set verify_ssl:false in the descriptor (pipeline passes it through) | Many NSO sites; Cote d'Ivoire
JS-challenge / SPA detail needs rendering | 200 empty body, or an ephemeral encrypted detail hash | Prefer the API; else find a DETERMINISTIC file path from a stable id (thumbnail/slug) | Cote d'Ivoire (thumbnail id -> PDF path)
Dead-looking domain (rebrand or hijack) | Old domain parked / SEO-spam / shared-hosting box | Web-search the agency's current name; try http:// and alternate TLDs | Burundi (ISTEEBU->INSBU), Cote d'Ivoire (ins.ci->anstat.ci)
Auth-gated API (401/403, no public token) | Every API route returns 401/403; no token in the client JS | Try the CENTRAL BANK (republishes the NSO CPI) before writing it off | Mozambique (solved via BM); Cabo Verde (still blocked)
Server genuinely down / regional outage | Times out from multiple network paths | Confirm globally down, check for a live alternate; retry later (needs calendar time) | Guinea-Bissau, Gabon, Eswatini, Djibouti
Opaque / no-filename download URL | URL ends /download or ?wpdmdl=; month not in filename | save_as in the discover block; read the report month from the document text | Congo, Chad, Burundi, Seychelles
Newest file not first; ids reset yearly | Bulletin numbering restarts each year; a listing lags | Always pick by parsed (year, month); union multiple listing pages | CAR, Chad, Congo
Messy PDF tables / wrapped labels | Function labels wrap over 1–3 lines; sub-items interleaved | Trailing-number anchor (nums[-4]/-3/-1); pending / prev+own+next label windows | CEMAC & WAEMU notes (Congo, CAR, Chad, Cameroon, Guinea)
Non-standard calendar (Ethiopian FY) | Dates tagged 'EFY 2018' with Gregorian month names | Convert (calendar fact, not estimation); anchor the last table row to the confirmed month | Ethiopia
Data only as charts / stale / annual | Divisions are bar charts; or only an annual/quarterly file | Capture the clean all-items headline; flag ⚠️ PARTIAL with the limitation documented | Liberia, Ethiopia, DR Congo
Excel quirks | Weight columns before the index block; stacked tables reuse codes; integer weights | Locate the date header row; first-occurrence dedup; sanity-check value magnitude | Mozambique, Seychelles, Lesotho
Tooling traps | Bash heredocs mangle regex; WP REST JSON escapes slashes; HTML-entity URLs | Write scripts to file; unescape \/ before URL match; percent-encode entities | (cross-cutting)

## 4. Outstanding & Next Steps
# | Country | ISO3 | Region / Bloc | Category | Reason outstanding | Recommended next step
1 | Guinea-Bissau | GNW | West Africa (WAEMU) | Server outage | NSO (INE) IHPC PDF exists but stat-guinebissau.com times out globally | Retry when server recovers (~15-min build; WAEMU format known). Thin fallbacks: BCEAO headline / MoF stale IHPC
2 | Gabon | GAB | Central Africa (CEMAC) | Server outage | NSO (DGSS) dgstat.ga unreachable; no live alternate domain | Retry later; or BEAC regional bulletin (headline only)
3 | Eswatini | SWZ | Southern (SADC) | Server outage | NSO (CSO) eswatinistats.org.sz unreachable | Retry later; CB/MoF publish only budget/headline
4 | Djibouti | DJI | Horn of Africa | Backend down | NSO Nuxt SPA -> Heroku API returns 404/500 (backend down) | Retry when backend recovers; MoF has no CPI
5 | Cabo Verde | CPV | West Africa/Islands | Auth-gated | NSO (INE) Angular API 401 everywhere, no token in client; CB/MoF publish no CPI file | Needs INE API credentials
6 | Comoros | COM | Southern/Islands | Weak partial only | NSO SPA shell; only CB quarterly bulletin (all-items IHPC, quarterly, sparse) | Optional ⚠️ partial from BCC bulletin if coverage required
7 | Sao Tome & Principe | STP | Central Africa/Islands | No online CPI | NSO Phoca-download categories empty; CB/MoF publish no CPI series | Monitor; likely needs direct request to INE
8 | Gambia | GMB | West Africa | No online CPI | NSO main site down; only a NADA microdata portal (no CPI series) | Retry NSO site; or request from GBoS
9 | Equatorial Guinea | GNQ | Central Africa (CEMAC) | No online CPI | NSO (INEGE) static shell, no files/API; CB is regional BEAC (headline only) | Monitor; BEAC headline as last resort
10 | Somalia | SOM | Horn of Africa | No online CPI | No NSO CPI; CB & MoF publish none | Out of reach
11 | Sudan | SDN | North/Horn | No online CPI (conflict) | CBOS/MoF have no CPI series online | Out of reach (conflict)
12 | South Sudan | SSD | East Africa | Stale only (conflict) | CB statistical bulletins stale to 2021 and broken PDFs | Out of reach (conflict)
13 | Eritrea | ERI | Horn of Africa | No online CPI | No NSO/CB/MoF CPI online | Out of reach
Legend: yellow = data exists, server temporarily down (retry later) ¦ blue = weak/partial fallback available ¦ red = no CPI published by NSO, central bank or finance ministry.